## Procurement plan 2025
Developing Climate Resilient Livelihoods in the Vulnerable Watershed in Nepal (DCRL in VWN) Project
Revised Procurement Plan 2025
Atlas Award ID if relevant: '00127610
Quantum Project ID: 00121535
Duration of this plan : 1 January to September 2025
UNSDCF/CPD Outcome: Outcome 3: By 2022, environment management, sustainable recovery and reconstruction and resilience to climate change and natural disaster are strengthened at all levels (SDGs 5, 6, 10, 11, 13, 15)
UNDP Strategic Plan (2018-2021): Building resilience to crises and shocks, in order to safeguard development gains. Signature solution 3: Enhance national prevention and recovery capacities for resilient societies Signature solution 4: Promote nature-based solutions for a sustainable planet.
CPD Output:
No. | Project | Quantum Task Num | Activity Number | Requisiton Number | UN ALL PRC number | Quantum Procurement Plan Reference | Description | Procurement Category (Method of Procurement - ITB/RFP/RFQ/PN ) | Quantity (A) | Unit | Per unit cost in USD (B) | Total amount in USD (A*B) | Type of Procurement | Procurement Service Category (IC, Service, Goods, Civil Works) | Expected Start Date (MM/DD/YYYY) | Expected Delivery Date (MM/DD/YYYY) | Contract End Date (MM/DD/YYYY) | Source of Fund | Status | Remarks
1 | DCRL | Required | 2.5.1 |  |  |  | Final Project Impact evaluation and report (Socio Economic analysis) | Direct Procurment | 1 | Report | 8778.81 | 8778.81 | Contratual service | Service | 2025-03-01 | 2025-06-30 | 2025-06-30 | GEF
2 | DCRL | Required | 3.1.15 |  |  |  | Project Audit | LTA/RFQ | 1 | Audit | 4379 | 4379 | Contratual service | Service | 2025-08-15 | 2025-09-30 | 2025-09-30 | GEF
3 | DCRL | Required | 1.4.6 |  |  |  | Hire a social and Environmental safeguard expert | LTA/IC | 1 | Report | 9750 | 9750 | IC | Service | 2025-01-07 | 2025-06-30 | 2025-06-30 | GEF
4 | DCRL | Required | 1.1.4 |  |  |  | Watershed Desktop establishment and application of assessment tool, guidelines and protocols in the lower dudkosi watershed | RFQ | 12 | Equipments | 6813.5833 | 81763 | Contratual service | Goods | 2025-02-03 | 2025-04-30 | 2025-04-30 | GEF
5 | DCRL | Required | 1.1.4 |  |  |  | Watershed Desktop establishment Equipments for DofSC | RFQ | 10 | Equipments | 5302.1 | 53021 | Contratual service | Goods | 2025-08-01 | 2025-09-30 | 2025-09-30 | GEF
6 | [6 empty] | Sharing Project Experience and dissemination of Climate Resilient Watershed management practices to federal, provincial and Local officials (Wrap up) | LTA/Direct | 1 | Event | 39371 | 39371 | Contratual service | Service | 2025-08-01 | 2025-09-30 | 2025-09-30 | GEF
7 | DCRL | Required | 2.5.7 |  |  |  | Prublication of UNDP Nature lesson from DCRL | PN/LTA | 1 | Lesson learnt sotory | 10000 | 10000 | IC | Service | 2025-08-01 | 2025-09-30 | 2025-09-30 | GEF
8 | DCRL | Required | 2.5.7 |  |  |  | Case Stories Publication/Lesson Learnt | PN/LTA | 1 | Stories Publication | 6479.84 | 6479.84 | IC | Service | 2025-08-01 | 2025-09-30 | 2025-09-30 | UNDP
9 | [6 empty] | Equipment support for Turmeric processing |  | 1 | Equipment | 9798 | 9798 | Contratual service | Goods | 2025-08-01 | 2025-09-30 | 2025-09-30
10 | DCRL | Direct from Project | 1.1.1 |  |  | 1.1.1 | Establishment of coordinaion meeting and platforms for IWM in Province Level | LTA/RFQ | 1 | Training workshop | 7532.0713 | 7532.0713 | Training, Workshops and Conference | Service | 2025-05-01 | 2025-08-30 | 2025-08-30 | GEF
11 |  |  | 1.1.4 |  |  | 1.1.4 | Watershed Desktop establishment and application of assessment tool, guidelines and protocols in the lower dudkosi watershed (Ref: 1.1.2 and1.1.3) | LTA/RFQ | 2 | Event | 6750 | 13500 | Training, Workshops and Conference | Service | 2025-08-01 | 2025-09-30 | 2025-09-30
12 |  |  | 1.1.4 |  |  | 1.1.4 | Watershed Desktop establishment and application of assessment tool, guidelines and protocols in the lower dudkosi watershed (Ref: 1.1.2 and1.1.3) | Micro Canvassing/RFP | 2 | Report | 3580.714 | 7161.428 | Contratual service | Service | 2025-08-01 | 2025-09-30 | 2025-09-30
13 |  |  | 1.1.4 |  |  | 1.1.4 | Interactive Panel Board | LTA/RFQ | 1 | Equipment | 4125.0581 | 4125.0581 | Contratual service | Goods | 2025-05-01 | 2025-08-30 | 2025-08-30
14 |  |  | 1.1.4 |  |  | 1.1.4 | Validation/Dissemination of watershed Atlas | LTA/RFQ | 2 | Event | 3921.0515 | 7842.103 | Training, Workshops and Conference | Service | 2025-05-01 | 2025-08-30 | 2025-08-30
15 |  |  | 1.2.3 |  |  | 1.2.3 | Advanced training on Design and Cost estimate for SCWM activities | LTA/RFQ | 1 | Event | 12278.6561 | 12278.6561 | Training, Workshops and Conference | Service | 2025-05-01 | 2025-08-30 | 2025-08-30
16 |  |  | 1.2.3 |  |  | 1.2.3 | Community orientation on SES, GRM and Health and safety to Pond user committee | LTA/RFQ | 1 | Event | 4414.2286 | 4414.2286 | Training, Workshops and Conference | Service | 2025-02-01 | 2025-04-30 | 2025-04-30
17 |  |  | 1.2.3 |  |  | 1.2.3 | Sharing Project Experience and dissemination of Climate Resilient Watershed management practices to federal, provincial and Local officials (Wrap up) | LTA/RFQ | 1 | Event | 5000 | 5000 | Training, Workshops and Conference | Service | 2025-08-01 | 2025-09-30 | 2025-09-30
18 |  |  | 1.2.3 |  |  | 1.2.3 | Learning & Interaction with ward chairperson, LOA partners and stakehodders on project sustainability | Micro Canvassing | 1 | Event | 4347.8261 | 4347.8261 | Training, Workshops and Conference | Service | 2025-08-01 | 2025-09-30 | 2025-09-30
19 |  |  | 1.2.3 |  |  | 1.2.3 | MHVR training for Palika Engineers | Micro Canvassing | 1 | Event | 4512.1044 | 4512.1044 | Training, Workshops and Conference | Service | 2025-05-01 | 2025-08-30 | 2025-08-30
20 |  |  | 2.1.2 |  |  | 2.1.2 | Watershed and Palika Level IWM Plan Sharing meeting (all four watershed) | LTA/RFQ | 2 | Event | 5815.9138 | 11631.8275 | Training, Workshops and Conference | Service | 2025-05-01 | 2025-08-30 | 2025-08-30
21 |  |  | 2.3.1 |  |  | 2.3.1 | Drone Operation skills and technique for aerial seeding event | LTA/RFQ | 1 | Event | 6888.1612 | 6888.1612 | Training, Workshops and Conference | Service | 2025-05-01 | 2025-08-30 | 2025-08-30
22 |  |  | 2.3.2 |  |  | 2.3.2 | Technical training to operators on operation, repair and maintenance of water lifting equipment and accessories. | LTA/RFQ | 1 | Event | 8078.9948 | 8078.9948 | Training, Workshops and Conference | Service | 2025-05-01 | 2025-08-30 | 2025-08-30
23 |  |  | 2.3.2 |  |  | 2.3.2 | Development of lifted water distribution system | RFQ | 1 | System | 23860.9759 | 23860.9759 | Training, Workshops and Conference | Service | 2025-08-01 | 2025-09-30 | 2025-09-30
24 |  |  | 2.3.2 |  |  | 2.3.2 | Water distribution pipe support to water lifting schemes | RFQ | 1 | System | 12000 | 12000 | System | Service | 2025-08-01 | 2025-09-30 | 2025-09-30
25 |  |  | 2.3.2 |  |  | 2.3.2 | Solar panels and accessories for Chyasmitar water lifting scheme | RFQ | 1 | System | 19188.005 | 19188.005 | System | Goods | 2025-06-01 | 2025-08-30 | 2025-08-30
26 |  |  | 2.3.2 |  |  | 2.3.2 | Electrification for Mangaltar water lifting scheme | RFQ | 1 | System | 36588.0221 | 36588.0221 | System | Goods | 2025-06-01 | 2025-08-30 | 2025-08-30
27 |  |  | 2.3.2 |  |  | 2.3.2 | Fencing operation and maintenance support | Micro Canvassing | 3 | Pond | 1396.2559 | 4188.7676 | Pond | Goods | 2025-06-01 | 2025-08-30 | 2025-08-30
28 | DCRL | Direct from Project | 2.3.3 |  |  | 2.3.3 | Provide farmer user groups with gender friendly, labor efficient agriculture tools (1 Group=10 HH) | RFQ | 1 | Tools | 4015.4482 | 4015.4482 | Training, Workshops and Conference | Service | 2025-05-01 | 2025-06-30 | 2025-06-30 | GEF
29 | DCRL | Direct from Project | 2.3.3 |  |  | 2.3.3 | Orientation for water lifting user committee and Palika Officials for operation and maintenance sustainability plan (5) | LTA/RFQ | 1 | Event | 4758.1197 | 4758.1197 | Training, Workshops and Conference | Service | 2025-06-01 | 2025-06-30 | 2025-06-30 | GEF
30 | DCRL | Direct from Project | 2.3.3 |  |  | 2.3.3 | Training on conservation farmining and agro-forestry including women friendly technologies and innovations (400 person) | LTA/RFQ | 1 | Event | 16767.7964 | 16767.7964 | Training, Workshops and Conference | Service | 2025-06-01 | 2025-06-30 | 2025-06-30 | GEF
31 | DCRL | Direct from Project | 2.3.5 |  |  | 2.3.5 | Material support to construct fuel efficient stoves | RFQ | 1 | Event | 18893.739 | 18893.739 | Contratual service | Service | 2025-06-01 | 2025-06-30 | 2025-06-30 | GEF
32 | DCRL | Direct from Project | 2.3.5 |  |  | 2.3.5 | National Workshop on degrated land restoration and drought management | LTA/RFQ | 1 | Event | 5245.306 | 5245.306 | Training, Workshops and Conference | Service | 2025-04-01 | 2025-06-30 | 2025-06-30 | GEF
33 | DCRL | Direct from Project | 2.3.5 |  |  | 2.3.5 | Survival status mapping of drought resistant species plantation on dryland | LTA/RFQ | 1 | Event | 3675.6455 | 3675.6455 | Training, Workshops and Conference | Service | 2025-06-01 | 2025-06-30 | 2025-06-30 | GEF
34 | DCRL | Direct from Project | 2.4.4 |  |  | 2.4.4 | Community/Palika level orienation and handover of sub projects (as per Implementation of exit strategy recommendation) | LTA/RFQ | 1 | Event | 22226.6272 | 22226.6272 | Training, Workshops and Conference | Service | 2025-04-01 | 2025-06-30 | 2025-06-30 | GEF
35 | DCRL | Direct from Project | 2.4.4 |  |  | 2.4.4 | Preparation of a handbook on tools and techniques on drought management | Micro Canvasing | 1 | Event | 2486.1668 | 2486.1668 | Training, Workshops and Conference | Service | 2025-04-01 | 2025-06-30 | 2025-06-30 | GEF
36 | DCRL | Direct from Project | 2.4.4 |  |  | 2.4.4 | GESI and Leadership training to local leaders/users committee | LTA/RFQ | 1 | Event | 4706.1386 | 4706.1386 | Training, Workshops and Conference | Goods | 2025-06-01 | 2025-08-30 | 2025-08-30 | GEF
37 | DCRL | Direct from Project | 2.5.1 |  |  | 2.5.1 | Project knowledge product | LTA/RFQ | 1 | Event | 11352.83 | 11352.83 | Printing and Publication | Goods | 2025-06-01 | 2025-08-30 | 2025-08-30 | GEF
38 | DCRL | Direct from Project | 2.5.1 |  |  | 2.5.1 | Province level Project sharing workshop ( Bagmati & Madhesh and Lumbini & Gandaki) | LTA/RFQ | 1 | Event | 11954.2473 | 11954.2473 | Training, Workshops and Conference | Goods | 2025-06-01 | 2025-08-30 | 2025-08-30 | GEF
39 | DCRL | Direct from Project | 2.5.1 |  |  | 2.5.1 | Development of project visibility materials including media mobilization | LTA/RFQ | 1 | Event | 7497.4097 | 7497.4097 | Printing and Publication | Goods | 2025-06-01 | 2025-08-30 | 2025-08-30 | GEF
40 | DCRL | Direct from Project | 2.5.1 |  |  | 2.5.1 | Video documentary preparation on project results | LTA/RFQ | 1 | Event | 5412.6771 | 5412.6771 | Video | Goods | 2025-06-01 | 2025-08-30 | 2025-08-30 | GEF
41 | DCRL | Direct from Project | 2.5.7 |  |  | 2.5.7 | Developmnet of IWM framework at national, Provincial and local levels | LTA/RFQ | 1 | Event | 2459.1844 | 2459.1844 | Training, Workshops and Conference | Goods | 2025-06-01 | 2025-08-30 | 2025-08-30 | GEF
42 | DCRL | Direct from Project | 2.5.7 |  |  | 2.5.7 | Skills development Training for local farmers | LTA/RFQ | 1 | Event | 3239.1656 | 3239.1656 | Training, Workshops and Conference | Goods | 2025-06-01 | 2025-08-30 | 2025-08-30 | GEF
43 | DCRL | Direct from Project | 2.5.7 |  |  | 2.5.7 | Equipment support to bamboo entrepreneurs | RFQ | 1 | Equipment | 5292.0495 | 5292.0495 | Contratual service | Goods | 2025-06-01 | 2025-08-30 | 2025-08-30 | GEF
44 | DCRL | Direct from Project | 2.5.7 |  |  | 2.5.7 | Equipment support for Tomato sauce making | RFQ | 1 | Equipment | 10339.7145 | 10339.7145 | Contratual service | Goods | 2025-06-01 | 2025-08-30 | 2025-08-30 | GEF
45 | DCRL | Direct from Project | 2.5.7 |  |  | 2.5.7 | Support to Executive committee for Gender Equality and women empowerment | LTA/RFQ | 1 | Event | 4627.2981 | 4627.2981 | Training, Workshops and Conference | Goods | 2025-05-20 | 2025-06-30 | 2025-06-30 | GEF
46 | DCRL | Direct from Project | 3 |  |  | 3 | Office supplies | LTA/RFQ | 1 | Regular | 5920.3371 | 5920.3371 | Supplies | Service | 2025-02-20 | 2025-09-30 | 2025-09-30 | GEF
47 | DCRL | Direct from Project | 3 |  |  | 3 | Office supplies | LTA/RFQ | 1 | Regular | 3000 | 3000 | Supplies | Service | 2025-04-01 | 2025-09-30 | 2025-09-30 | UNDP
48 | DCRL | Direct from Project | 3 |  |  | 3 | Repair and servicing vehicle, photocopy machine, laptop, computer accessories, fuels for vehicle and accessories etc | LTA/RFQ | 1 | Event | 32289.854 | 32289.854 | Contratual service | Goods | 2025-01-20 | 2025-06-30 | 2025-06-30 | GEF
49 | DCRL | Direct from Project |  |  |  |  | LOA with Partners | LOA | 1 | Services | 325722 | 467769 | LOA | Service | 2025-02-02 | 2025-06-30 | 2025-06-30 | GEF
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be updated once the plan is entered into Quantum.
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be updated once the plan is entered into Quantum.

## Category (hidden)
Procurement Plan Category: | Unit | Team/Unit | Exp. Procurement Process: |  | Evaluation Score:
Communication & AudioVisual Eqp | Book | ICT | Competitive exercise |  | Lowest Price among Responsive Offer
Construction/Works and Refurbishments | Box | Admin | Call-off order (LTA) |  | Cumulative Analysis
International Individual Contractors | Case | HR | Direct contracting |  | Lowest Price Technically Compliant
Internet/Web Design Services | Day | Finance | Amendment
Local Individual Contractors | Each |  |  |  | Review Committee:
Motor Vehicles | Hour | Advertising: | Solicitation: |  | Not required
Office Furniture and Fixtures | Month | Website | Micro-Purchasing |  | CAP
Office Machinery and Equipment | Pairs | UNGM | RFQ |  | RACP
Office Supplies | Pax | Local Media | RFP |  | ACP
Other Goods/Assets and Commodities | Pcs | Int' Media | ITB
Other Services - Companies | Set
Printing & Publications Services | Time |  |  |  | RNE
Rental of Equipment | Lump Sum |  | Contract Modality: | Procurement Service Category | RNE-E
Rental of Premises |  |  | Goods | Construction Engineering | RNE-FS
Safety and Security Equipment |  |  | Services | Consulting Services | UNDP
Safety and Security Services |  |  | Civil Works | Elections
Software Development Services |  |  | Responsible Party Engagement | Environmental & Energy
Software Lincenses |  |  | Individual Contract | Health
Training/Workshop/Meeting/Conf Services |  |  | Staff | Livelihoods
Consultancy Services - Firm |  |  |  | General Operations
Translation Services |  |  |  | Technology
Travel Services |  |  |  | Transportation Services
HR Plan |  |  |  | Vehicles
Other
CCO's Spending Plan Category:
Graphic and Design services
Advertising/Announcement Services
Catering Services
ICT Equipment and supplies
Telecommunication Services
Insurance Services
HR
Audit Services
Support Cost
Staff Learning
Travel allowances (DSA. terminals)
Travel Tickets
SLA
LOA
PCA